# Appendix A: Data Description

## A.1 Data Sources

### Quarterly Performance Reports (QPR)

The QPR data is extracted from HUD’s DRGR (Disaster Recovery Grant Reporting) system. This administrative data captures:

- Fund allocations by appropriation

- Obligation, disbursement, and expenditure amounts

- Activity types (housing, infrastructure, economic development, planning, administration)

- Quarterly reporting periods (2003-2023)

The raw dataset contains 130,605 quarterly observations across 78 unique grantees and 206 grant allocations.

### Population Data

Population figures are obtained from:

- U.S. Census Bureau decennial census (2000, 2010, 2020)

- American Community Survey estimates for intercensal years

### Disaster Characteristics

Disaster type classifications derive from:

- FEMA declared disaster data

- Primary hazard type (hurricane, wildfire, flood, other)

- Disaster declaration date for era classification

### Experience Indicators

Grantee experience measures are computed from:

- Count of prior CDBG-DR grants managed

- Binary classification: Novice (first CDBG-DR grant) vs. Experienced (2+ prior grants)

## A.2 Spending Velocity Construction

### The Dynamic Denominator Problem

Initial velocity calculations using period-specific denominators produced computational artifacts. When the denominator (obligated amount) changes across periods, apparent velocity changes reflect administrative adjustments rather than actual spending acceleration:

Velocitytraw=ExpendedtObligatedt−Expendedt−1Obligatedt−1

This formula produces spurious velocity when obligations change. For example, if Obligated doubles from quarter t−1 to t while Expended increases moderately, the ratio drops despite actual spending increases.

### Standardized Velocity with Fixed Denominators

The standardized approach uses the final obligated amount as a stable denominator:

Velocitytstd=ExpendedtObligatedfinal−Expendedt−1Obligatedfinal

This ensures that velocity changes reflect only changes in the numerator (actual expenditure), not administrative adjustments to obligations.

### Impact of Standardization

| Metric | Raw Velocity | Standardized Velocity | Reduction |
| --- | --- | --- | --- |
| Std Dev | 0.089 | 0.028 | 68.5% |
| Extreme values (> | 0.10 | ) | 0.60% |
| IQR | 0.031 | 0.012 | 61.3% |

The standardized approach dramatically reduces measurement noise while preserving meaningful velocity variation.

### Winsorization

Standardized velocity values are winsorized at the 1st and 99th percentiles to limit outlier influence:

Velocitywinsorized=P1if Velocity<P1P99if Velocity>P99Velocityotherwise

This bounds extreme observations while preserving the full distribution shape.

## A.3 Phase-Specific Velocity

Programs are divided into temporal terciles based on elapsed quarters:

- Early phase: Quarters 1 through ⌊T/3⌋

- Middle phase: Quarters ⌊T/3⌋+1 through ⌊2T/3⌋

- Late phase: Quarters ⌊2T/3⌋+1 through T

where T is the total number of observed quarters.

Mean velocity within each phase creates phase-specific measures:

Velocityphase=1Nphaset∈phase​Velocityt

## A.4 Sample Characteristics

### Overall Sample Composition

| Characteristic | Count | Percent |
| --- | --- | --- |
| Total Observations | 152 | 100.0% |
| Unique grantees | 78 | – |
| Unique disaster events | 18 | – |
| Unique grant allocations | 206 | – |

### Government Type Distribution

| Government Type | N | Percent |
| --- | --- | --- |
| State governments | 37 | 24.3% |
| Local governments | 40 | 26.3% |
| Multiple/Mixed | 75 | 49.3% |
| Total | 152 | 100.0% |

### Disaster Type Distribution

| Disaster Type | N | Percent |
| --- | --- | --- |
| Hurricane | 89 | 58.6% |
| Flood | 27 | 17.8% |
| Wildfire | 24 | 15.8% |
| Other | 12 | 7.9% |
| Total | 152 | 100.0% |

### Experience Distribution

| Experience Level | N | Percent |
| --- | --- | --- |
| Novice (first CDBG-DR) | 74 | 48.7% |
| Experienced (2+ prior) | 78 | 51.3% |
| Total | 152 | 100.0% |

### Program Type Distribution

| Primary Program Type | N | Percent |
| --- | --- | --- |
| Housing | 67 | 44.1% |
| Infrastructure | 41 | 27.0% |
| Administration | 34 | 22.4% |
| Other | 10 | 6.6% |
| Total | 152 | 100.0% |

### Censoring Status

| Status | N | Percent |
| --- | --- | --- |
| Completed (reached 95% expenditure) | 40 | 26.3% |
| Right-censored (not yet complete) | 112 | 73.7% |
| Total | 152 | 100.0% |

The high censoring rate (73.7%) motivates survival analysis methods. Standard regression approaches that drop censored observations would discard 112 of 152 observations, severely limiting statistical power and introducing selection bias.

## A.5 Velocity Summary Statistics

| Variable | N | Mean | SD | Min | Median | Max |
| --- | --- | --- | --- | --- | --- | --- |
| Overall Velocity (pp/quarter) | 152 | 2.14 | 1.83 | 0.12 | 1.67 | 9.84 |
| Early Phase Velocity | 152 | 2.89 | 2.41 | 0.08 | 2.21 | 12.67 |
| Middle Phase Velocity | 152 | 1.92 | 1.76 | 0.04 | 1.48 | 8.93 |
| Late Phase Velocity | 152 | 1.61 | 1.89 | 0.02 | 1.12 | 11.24 |
| Duration (quarters, completed only) | 40 | 68.2 | 28.4 | 18 | 63.5 | 142 |

Key observations:

- Overall velocity averages 2.14 percentage points per quarter, indicating that the typical grantee expends approximately 2% of their total allocation each quarter.

- Phase pattern: Velocity is highest in early phases (2.89 pp/quarter) and declines through middle (1.92) and late (1.61) phases, consistent with front-loaded activity followed by closeout delays.

- Substantial variation exists across grantees (SD = 1.83 for overall velocity), providing analytic leverage for detecting velocity-completion associations.

- Completion timing: Among the 40 completed programs, median time to 95% completion is 63.5 quarters (approximately 16 years).

## A.6 Data Quality

Quality assurance flags track potential measurement issues:

| QA Flag | N | Percent |
| --- | --- | --- |
| Extreme velocity ( | v | > 10 pp/quarter) |
| Large obligation adjustment (>25%) | 12 | 7.9% |
| Negative expenditure adjustment | 8 | 5.3% |

Sensitivity analyses excluding flagged observations produce substantively similar results (see Appendix C).

## A.7 Disaster Coverage

The sample covers 18 major disaster events from 2003 to 2023:

Hurricane Events: - Hurricane Katrina (2005): Gulf Coast states - Superstorm Sandy (2012): Mid-Atlantic and Northeast - Hurricane Harvey (2017): Texas coast - Hurricane Maria (2017): Puerto Rico and U.S. Virgin Islands - Hurricane Irma (2017): Florida and Caribbean

Wildfire Events: - California Wildfires (2017-2020): Multiple events - Colorado Fires (2012-2013) - Arizona Wildfires (2011)

Flood Events: - Louisiana Floods (2016) - Colorado Floods (2013) - Multiple smaller flood events

Other Events: - Joplin Tornado (2011) - Oklahoma Tornadoes (2013) - Various smaller disasters

The diversity of disaster types, geographic locations, and governmental structures provides variation needed to test context-specific velocity effects.